## Project Design and Data Plan
TEMPLATE 3 Tab 1: PROJECT DESIGN STATEMENT
Company name: | Cartagena On Chain
Note: it is mandatory to complete columns C-F for each Activity you propose. Incomplete project designs will not be scored.
Timeline | Tasks | Expected Changes/Targets | Signs of Success | What data will be generated? | Key Personnel Responsible
|  | What will be different once the activity is done? (Provide specific numbers where possible.) | What will you measure to assess whether the activity was completed and the desired outcome achieved? Please specify the numeric targets for your expected outcomes (e.g., number of users). Each activity must have at least one measurable outcome. | Each activity needs to generate specific types of data. For example: (1) During software development, there may be GitHub commits or version control logs; during content creation, the volume of digital materials will increase. (2) During piloting, you can track user numbers, user feedback, and updates to code or design. (3) During implementation, you can monitor new user registrations or deployment progress via online tracking tools. We require each activity to produce real-time data that is accessible through internet-based tools (e.g., dashboards, trackers, APIs). Please indicate what data will be generated per activity, how it will be collected, and how it will be accessed. | Who is responsible for each task? Refer to the funding agreement for the definition of 'Key Personnel' and details on who may be included. Name and role in the team.
Quarter 1 (of the funded period)
Milestone 1 | Engineering rigor & ERC-20 pool deployment | Repo verifiably trustworthy: CI fails on test failures, coverage reports published, and the ERC-20 (stablecoin) pool deployed to mainnet — the version actually relevant to humanitarian cash transfers. | (i) solidity-coverage report published, ≥80% on critical paths. (ii) ERC-20 pool deployed and verified on explorer. (iii) Contract CI job green on every PR (already in place). | GitHub Actions logs, coverage HTML report (gh-pages), deployment tx hashes, verified contract on explorer. | Carlos Quintero (Co-founder, backend & contracts)
Activity 1 | Activity 1 — CI test masking was corrected pre-submission (contract CI job added, `¦¦ true` removed). Remaining Q1 work: install solidity-coverage; publish first coverage report; target ≥80% on critical withdrawal/ragequit paths. | Coverage tooling shipped; coverage badge visible in README. | Coverage ≥80% on critical paths. | PR diffs, coverage report URL, GitHub Actions config. | Carlos Quintero
Activity 2 | Activity 2 — Deploy GaleonPrivacyPoolComplex (ERC-20) to mainnet for USDC and USDT; integrate with Entrypoint; run end-to-end deposit + withdrawal test against live contracts. | ERC-20 pool live on mainnet; one full deposit→withdrawal cycle completed with USDC. | Verified contract address on explorer; test tx hashes documented. | Deployment scripts, contract address, tx hashes for round-trip test. | Carlos Quintero
Milestone 2 | External security audit kickoff | Independent audit engaged covering Galeon-specific custom modifications (GaleonRegistry, Entrypoint ASP changes, UUPS upgrades) and the stealth-address library. 0xbow upstream privacy-pool circuits are already Oxorio-audited and out of scope. | Signed audit engagement letter; published scope-of-work; auditor on-boarded to frozen branch. | RFP responses (PDFs), comparison matrix, signed contract, scope document. | Mateo Daza (technical lead) + Juan David Correa (project coordination)
Activity 1 | Activity 1 — Solicit proposals from 3 audit firms (e.g., Spearbit, Zellic, Oxorio for delta scope), select winner. | Contract signed by end of Q1. | Auditor engagement signed. | RFPs, comparison matrix, signed engagement letter. | Mateo Daza
Activity 2 | Activity 2 — Freeze audit branch (`audit-v1`); produce threat model and a clear diff of our modifications relative to upstream 0xbow. | Audit-ready branch tagged with complete documentation. | Threat-model document + custom-modification diff published. | Git tag, threat-model.md, modifications-diff.md. | Carlos Quintero
Milestone 3 | Partner discovery, LOI, and operational model scoping | Identify the first plausible pilot site through structured discovery. Produce an operational dependency model: who handles KYC/beneficiary enrollment, cash-out/off-ramp, lost-access recovery, sanctions false positives, and beneficiary support. These are partner responsibilities, not Galeon's, but must be scoped before any pilot. | One signed LOI from a UNICEF country office or NGO partner; operational dependency model documented with named partner responsibilities. | Discovery notes (with consent), partner-fit matrix, LOI document, operational-dependency-model.md. | Fabio Anaya (Growth lead) + Mateo Daza + Juan David Correa (project coordination)
Activity 1 | Activity 1 — Discovery sessions with 3-5 UNICEF country offices and 2-3 NGO partners; document fit, regulatory environment, on/off-ramp availability per geography. | Discovery completed with at least 5 organisations. | Discovery report with shortlisted partner-fit ranking. | Notes, partner-fit matrix. | Fabio Anaya + Mateo Daza
Activity 2 | Activity 2 — Convert top-ranked organisation into a signed LOI scoped to a ≤50-beneficiary Q3 controlled pilot. Draft operational dependency model with the partner: KYC (partner), off-ramp/cash-out (partner + licensed provider), lost-access/SIM-swap recovery (Privy + partner), liquidity (partner), sanctions false-positive appeals (Galeon ASP policy), beneficiary support (partner). | One LOI signed; operational dependency model drafted. | Signed LOI; operational model reviewed by partner. | LOI PDF, operational-dependency-model.md. | Fabio Anaya + Mateo Daza
Milestone 4 | Beneficiary onboarding — embedded email-based wallet (Privy) + account abstraction | First-time users receive a wallet via email login, never see seed phrases, and do not pay or manage gas fees. Account abstraction enables partner-sponsored gas, batched operations, and email/social recovery. The goal: a beneficiary opens a link, logs in, receives stablecoins — and does not need to know they are using crypto until they have the balance. Mobile-first design throughout (most beneficiaries access via phone). | End-to-end flow on mobile: invite link → email login → first stablecoin payment received, completed in <5 minutes by a non-crypto tester. Gas sponsored by partner; no seed phrase shown. | Frontend code (apps/web/app/setup), test recordings with consent, mobile-flow task-completion metrics, partner-sponsor gas configuration. | Mateo Daza
Activity 1 | Activity 1 — Integrate Privy embedded-wallet SDK with email recovery and account abstraction (smart wallet, gas sponsorship hooks) into the Setup flow. | Embedded wallet on staging; recovery path tested by two team members. | Working flow on staging. | PR diffs, integration test logs. | Mateo Daza
Activity 2 | Activity 2 — Mobile-first redesign of Setup, Receive, Pay, and Collect for non-technical first-time users on smartphones (large touch targets, clear copy, illustrated steps, no crypto jargon visible). | Redesigned pages shipped to staging. | Internal review passes; 5-user pre-test shows ≥80% task completion. | Figma file, PR diff, pre-test notes. | Mateo Daza
Milestone 5 | N/A | N/A | N/A | N/A | N/A
Activity 1 | N/A | N/A | N/A | N/A | N/A
Activity 2 | N/A | N/A | N/A | N/A | N/A
Q1 Key Deliverables
Front-end | Front-end: Privy embedded-wallet onboarding live in staging; redesigned Setup/Receive/Pay/Collect for non-technical users. | Live on staging. | Internal pre-test ≥80% task completion. | GitHub repo, Vercel preview URL. | Mateo Daza
Backend | Backend: ERC-20 stablecoin pool deployed and verified on Mantle Mainnet. CI hardened (no `¦¦ true`). Coverage report published. Audit engaged with frozen branch. One LOI from prospective pilot partner. | All five items completed in Q1. | Block-explorer verified contract; green CI on failures; coverage ≥80%; signed audit contract; signed LOI. | Contract address, CI logs, coverage URL, audit contract (redacted), LOI (PDF). | Carlos Quintero
Quarter 2 (of the funded period)
Milestone 1 | Real ASP filtering — sanctions screening + blocklist (replaces hackathon auto-approve) | The ASP service stops auto-approving every deposit. New approval pipeline checks each deposit label against a sanctions list (e.g., OFAC SDN) and a project-maintained blocklist; rejected labels are publicly logged. | Production ASP rejects at least one test-injected sanctioned address; published ASP policy document; first IPFS-published attestation tree. | ASP service code, screening provider integration (e.g., Chainalysis Address Screening, Elliptic Navigator), rejection logs, policy doc, IPFS CID of attestation tree. | Carlos Quintero
Activity 1 | Activity 1 — Select & integrate a screening provider (Chainalysis / Elliptic / TRM Labs free tier or open-source list like OFAC SDN); design rejection-handling protocol that preserves the anonymity set for non-rejected labels. | Screening provider integrated; rejection protocol documented. | Integration tests cover: (i) clean address approved, (ii) sanctioned address rejected, (iii) borderline address flagged for manual review. | PR diffs, provider contract / API credentials handling docs, test logs. | Carlos Quintero
Activity 2 | Activity 2 — Publish ASP policy (what is screened, how, who can appeal); start publishing ASP attestation trees on IPFS with the CID stored on-chain via the existing Entrypoint hook. | Policy published; first 5 weekly attestation trees on IPFS. | Policy document live; on-chain root-update events include real IPFS CIDs. | ASP-policy.md, IPFS CIDs, on-chain tx hashes. | Carlos Quintero
Milestone 2 | Audit findings remediated; report published | All critical and high audit findings resolved; auditor's letter of resolution published. | Zero open critical/high findings; auditor sign-off. | Audit-report.pdf, remediation tracker, commit references, letter of resolution. | Carlos Quintero + Mateo Daza + Juan David Correa (remediation tracking)
Activity 1 | Activity 1 — Triage findings, assign owners, plan remediation. | Triage spreadsheet signed off by auditor. | Triage complete. | GitHub issues per finding. | Carlos Quintero
Activity 2 | Activity 2 — Implement fixes; request auditor re-review; publish final report. | All critical & high closed. | Letter of resolution signed. | Audit report PDF, letter of resolution, PR diffs. | Carlos Quintero
Milestone 3 | Children's data protection — DPIA & in-product safeguards | Galeon implements documented in-product controls for any Port used in a program targeting minors (config flag, audit log, exclusion from public aggregates, data-minimisation contract with implementing partner). | Published DPIA aligned with UNICEF's Manual on Ethical Standards in Evidence Generation; technical controls live in production; first-party legal review. | DPIA document, code commits implementing the `children_program_mode` flag, audit-log schema, partner data-minimisation contract template. | Mateo Daza + external privacy counsel
Activity 1 | Activity 1 — DPIA scope and writing, engaging external privacy counsel familiar with UNICEF guidance. | Published DPIA. | Counsel sign-off. | DPIA PDF. | Mateo Daza + counsel
Activity 2 | Activity 2 — Implement `children_program_mode` flag at the API boundary; exclude flagged Ports from public dashboards and shareable reports; ship audit-log surface for implementing partners. | All in-product controls live in production. | End-to-end test verifies the flag cannot be bypassed by frontend changes. | PR diffs, integration tests, audit-log schema. | Mateo Daza + Carlos Quintero
Milestone 4 | Public open-source release (month-six commitment) | All Galeon code released under permissive licences (MIT for apps/libs, Apache-2.0 for contracts/pool SDK) by month six of the funded period, per UNICEF open-source requirements. CONTRIBUTING.md and CODE_OF_CONDUCT.md in place. From public GitHub release through contract end plus 12 months, Project Data will remain accessible in real time with 99% uptime. | Public GitHub organisation live; contribution guide and code of conduct published; secrets scan clean. | Public-repo URL, CONTRIBUTING.md, CODE_OF_CONDUCT.md, TruffleHog secrets-scan report. | Mateo Daza + Juan José Sanfeliú (community engagement)
Activity 1 | Activity 1 — Final security review, secrets audit (TruffleHog), license-header sweep across all packages. | Repository cleared for public release. | Audit checklist completed; secrets scan clean. | Checklist, TruffleHog report, license-header diff. | Carlos Quintero
Activity 2 | Activity 2 — Migrate monorepo to public GitHub organisation; publish announcement; archive private repo. | Public repo live; announcement published. | Public visibility on github.com. | Public-repo URL, announcement post. | Mateo Daza + Juan José Sanfeliú (announcement, community engagement)
Milestone 5 | Sandbox testing with partner staff (no real beneficiaries) | 3-5 partner staff complete the full flow (Port creation, stablecoin deposit, ZK withdrawal, Shipwreck report) in a staging environment using test tokens. Operational runbook validated. | All partner staff complete the flow end-to-end; zero-blocker issues in the runbook. | Sandbox test recordings (consent), runbook, issue tracker, staff feedback notes. | Mateo Daza + Fabio Anaya + Juan David Correa (runbook + coordination) + partner program officer
Activity 1 | Activity 1 — Set up staging environment mirroring production; create test-token faucet; prepare training materials. | Staging environment live with test tokens. | Staging URL accessible by partner staff. | Staging URL, training slides, test-token faucet. | Carlos Quintero
Activity 2 | Activity 2 — Moderated sandbox sessions with 3-5 partner staff; iterate on runbook based on feedback. | 5 sessions completed; runbook updated. | Staff can operate independently. | Session recordings, updated runbook, feedback log. | Mateo Daza
Q2 Key Deliverables
Front-end | Front-end: `children_program_mode` controls live; improved Pay and Collect; Privy integration tested in sandbox. | Live in production and staging. | In-product controls verified by tests; sandbox testing passed. | GitHub repo, Vercel build. | Mateo Daza
Backend | Backend: Real ASP filtering live (sanctions + blocklist + IPFS attestation); audit closed with letter of resolution; DPIA published; repo public by month six; partner staff validated in sandbox. | Five items complete. | First sanctioned-address test rejection; auditor letter; DPIA published; public repo live; sandbox sign-off. | ASP code + IPFS CIDs, audit letter, pilot dashboard, DPIA PDF. | Carlos Quintero
Quarter 3 (of the funded period)
Milestone 1 | Controlled pilot launch with LOI partner (≤50 beneficiaries) | First real-world cohort: 25-50 stablecoin transfers to verified beneficiaries, in close coordination with the LOI partner. Port labels use non-identifying operational codes (e.g., PORT-001) — no beneficiary names on-chain. | ≥25 verified beneficiary transactions; ≥90% recipient confirmation within 48h; satisfaction survey returned by ≥50% of cohort. | Anonymised aggregate metrics, recipient survey results, incident log, Port-label policy document. | Mateo Daza + Fabio Anaya + Juan David Correa (project coordination) + partner program officer
Activity 1 | Activity 1 — Production pilot deployment: dedicated PostgreSQL, monitoring (Sentry + Better Stack), uptime alerting, documented runbook for partner staff. | Pilot environment live, monitored, with documented runbook. | 30-day uptime ≥99%. | Status-page URL, runbook, incident log. | Carlos Quintero
Activity 2 | Activity 2 — Onboard first cohort of beneficiaries via partner staff; monitor transactions; collect feedback after 2 weeks. | 25-50 beneficiaries onboarded and transacting. | ≥25 verified transactions; partner staff operating independently with on-call support. | Transaction metrics, feedback survey, incident log. | Mateo Daza + partner staff
Milestone 2 | Shipwreck jurisdiction expansion and multi-language UI (English + one pilot language) | Shipwreck reports added for the pilot jurisdiction. Hardcoded FX rates replaced with live oracle. Frontend localised to English plus the pilot partner's working language. If the partner's language is Spanish, that counts; otherwise Spanish is not added in this phase. | i18n strings extracted; 2 languages live (EN + pilot language); native-speaker QA passed; 3 jurisdictions in Shipwreck (US, CO, + pilot); live FX oracle in production. | i18n bundles, QA reports, per-jurisdiction templates, oracle integration code. | Mateo Daza + Carlos Quintero + translation vendor
Activity 1 | Activity 1 — Extract all user-facing strings using next-intl; engage translation vendor for the pilot-partner language; integrate and QA. | One additional language bundle (pilot language) shipped and QA'd. | Native-speaker QA passed. | i18n EN bundle, pilot-language bundle, QA sign-off sheet. | Mateo Daza + vendor
Activity 2 | Activity 2 — Add pilot-jurisdiction Shipwreck template + EU baseline; integrate live FX oracle (Chainlink or CoinGecko API); validate with local advisor. | New templates live; live FX in production. | Sample PDFs validated by local advisors. | Code commits, sample PDFs, oracle integration tests. | Carlos Quintero + advisors
Milestone 3 | Pilot validation and feedback | 15 beneficiaries from the pilot cohort + 3-5 partner staff complete structured feedback. Top issues triaged for Q4. All beneficiary research requires ethics/safeguarding clearance and consent/assent instruments approved before data collection begins. | SUS ≥65; qualitative themes documented; top 5 issues triaged. | Ethics clearance documentation, consent/assent instruments, survey results (anonymised), interview notes, issue tracker. | Mateo Daza
Activity 1 | Activity 1 — Obtain ethics/safeguarding clearance for beneficiary research; prepare consent/assent instruments; conduct structured interviews with pilot beneficiaries and partner staff. | 20 sessions completed. | SUS ≥65; bug list triaged. | Recordings (consent given), synthesis report. | Mateo Daza
Activity 2 | Activity 2 — Targeted first-click tests on Pay and Collect in pilot language. | 100+ test responses. | Direct-success rate ≥70%. | Maze.co reports. | Mateo Daza
Milestone 4 | N/A | N/A | N/A | N/A | N/A
Activity 1 | N/A | N/A | N/A | N/A | N/A
Activity 2 | N/A | N/A | N/A | N/A | N/A
Milestone 5 | N/A | N/A | N/A | N/A | N/A
Activity 1 | N/A | N/A | N/A | N/A | N/A
Activity 2 | N/A | N/A | N/A | N/A | N/A
Q3 Key Deliverables
Front-end | Front-end: Controlled pilot live (≤50 beneficiaries); multi-language UI (English + pilot-partner language); localised Pay/Collect flows tested with real beneficiaries. | Live in production. | Pilot SUS ≥65; native-speaker QA passed. | GitHub repo, Vercel build, QA sheets. | Mateo Daza
Backend | Backend: Pilot environment monitored (≥99% uptime); live FX oracle for Shipwreck; pilot-jurisdiction compliance template added. Note: Q3/Q4 research load (interviews, Maze tests, evaluation, accessibility audit) requires translation vendor, UX research contractor, and partner staff support. | All items live. | ≥25 verified transactions; advisor sign-offs on compliance templates; uptime ≥99%. | Code, dashboards, advisor reviews. | Carlos Quintero
Quarter 4 (of the funded period)
Milestone 1 | Pilot expansion to ≤100 beneficiaries | Scale the controlled pilot from ≤50 to ≤100 beneficiaries, incorporating Q3 feedback. Address top 5 issues from Q3 validation. | ≥75 verified beneficiary transactions; ≥90% recipient confirmation within 48h; SUS ≥70. | Aggregate metrics, updated survey results, incident log. | Mateo Daza + Fabio Anaya + partner
Activity 1 | Activity 1 — Implement top 5 fixes from Q3 feedback; expand partner staff training for larger cohort. | All critical fixes shipped; additional staff trained. | Fix verification tests passing; staff sign-off. | PR diffs, training logs. | Carlos Quintero + Mateo Daza
Activity 2 | Activity 2 — Onboard second cohort (up to 50 additional beneficiaries); monitor for 30 days. | Second cohort transacting with ≤48h confirmation rate ≥90%. | 30-day uptime ≥99.5%. | Transaction metrics, status page, incident log. | Mateo Daza + partner
Milestone 2 | Independent implementation and usability evaluation | External evaluator assesses: usability (task completion, comprehension), support burden (incidents per beneficiary, escalation rate), partner workflow fit (staff time per cohort, runbook adherence), and incident rate. Ethics/safeguarding clearance renewed for expanded cohort. Joint evaluation report with partner. | External evaluator report delivered; measures usability, comprehension, support burden, incident rate, and partner workflow fit. | Evaluation methodology, anonymised dataset, implementation-evaluation.pdf, lessons-learned. | Mateo Daza + Fabio Anaya + external evaluator + partner M&E lead
Activity 1 | Activity 1 — Engage independent evaluator (e.g., 60 Decibels or local research firm) to assess usability, comprehension, support burden, and partner workflow fit. | Evaluation completed. | Evaluator report delivered. | Assessment instruments, raw data (anonymised), evaluation report. | Mateo Daza + evaluator
Activity 2 | Activity 2 — Publish implementation-evaluation.pdf jointly with partner; include lessons learned and recommendations for next phase. | Evaluation report published. | Joint partner + Galeon publication. | implementation-evaluation.pdf, blog post. | Mateo Daza + partner comms
Milestone 3 | Developer documentation & integration guides | Complete developer docs at docs.galeon.finance covering protocol concepts, API reference, and 2 integration tutorials. Aiming for first external developer to successfully integrate. | Docs site live; 2 end-to-end integration tutorials published; ≥1 external developer completes a tutorial. | Docs site URL, tutorial completion logs, first external integration PR/repo. | Mateo Daza + Juan José Sanfeliú (developer relations and content)
Activity 1 | Activity 1 — Write protocol overview, API reference, security model section, FAQ. | All sections published. | Internal review completed. | Docs site repo. | Mateo Daza
Activity 2 | Activity 2 — Two end-to-end tutorials: (i) Accept private stablecoin donations on a website, (ii) Run a screening ASP attestor. | 2 tutorials published; at least one external completion. | External developer feedback captured. | Tutorial pages, demo-app repos, feedback log. | Mateo Daza + Carlos Quintero + Juan José Sanfeliú (developer outreach)
Milestone 4 | Sustainability roadmap and partner engagement for post-funding viability | Concrete sustainability plan beyond the funded period: revenue mechanism configured on production; first prospective partners engaged; long-term financial plan delivered. | Revenue mechanism configured on production; ≥3 prospective partners in active conversation; sustainability plan delivered. | Sustainability plan document, prospect-pipeline doc (redacted), on-chain configuration evidence. | Mateo Daza + Fabio Anaya (partner engagement) + Juan José Sanfeliú (communications)
Activity 1 | Activity 1 — Configure revenue mechanism on production; document operating model. | Revenue mechanism live. | Production configuration verified on-chain. | Configuration evidence, tx hashes. | Carlos Quintero
Activity 2 | Activity 2 — Open conversations with 3-5 organisations (NGOs, foundations, donor platforms) about paid ASP-attestation tiers; document interest and objections. | 3-5 conversations completed. | Pipeline document with interest signal and feedback. | Pipeline doc (redacted), call notes. | Fabio Anaya + Juan José Sanfeliú + Mateo Daza
Milestone 5 | Final validation & accessibility | Closing round of validation across personas + accessibility conformance pass. Research sessions, Maze testing, and accessibility audit require vendor and partner support; this dependency is built into the Q4 timeline and staffing plan. | SUS ≥75 across personas; WCAG 2.1 AA conformance on the key user flows. | Recordings, SUS scores, accessibility audit report. | Mateo Daza + external accessibility auditor
Activity 1 | User testing — Product. Final moderated sessions across beneficiary + program officer. | 30 sessions. | SUS ≥75. | Synthesis report. | Mateo Daza
Activity 2 | Accessibility audit. Third-party WCAG 2.1 AA audit on Setup, Pay, Collect, Reports. | Conformance achieved on key flows. | Conformance report passed. | Audit report, axe-core CI results. | Mateo Daza
Q4 Key Deliverables
Front-end | Front-end: Pilot scaled to ≤100 beneficiaries with Q3 feedback addressed; WCAG 2.1 AA conformance on key flows. | Live in production. | SUS ≥70; accessibility audit passed. | Public repo, docs site, accessibility-report.pdf. | Mateo Daza
Backend | Backend: Implementation and usability evaluation published with partner; sustainability roadmap with revenue mechanism live and first prospects engaged; dev docs at docs.galeon.finance. | All items complete. | Evaluation report published; revenue mechanism live; docs site live. | Sustainability plan, prospect pipeline, implementation-evaluation.pdf. | Carlos Quintero + Mateo Daza
List all new product features that will be developed in the one-year investment period:
1. ERC-20 stablecoin pool deployed to mainnet (the version needed for humanitarian cash transfers).
2. Real ASP filtering: sanctions screening + blocklist + IPFS-published attestation (replaces hackathon auto-approve stub).
3. Children's data protection controls (`children_program_mode` flag, audit log, exclusion from public aggregates, DPIA).
4. Embedded email-based wallet (Privy) + account abstraction + mobile-first UX for non-crypto-literate beneficiaries (no seed phrases, no gas, mobile-optimised).
Please list all Open Source components generated through the workplan:
(i) ASP screening & attestation pipeline (sanctions + blocklist + IPFS publishing) — Apache-2.0.
(ii) `children_program_mode` API controls and audit-log surface — MIT.
(iii) Embedded-wallet + account-abstraction onboarding integration and mobile-first low-literacy UI components — MIT.
(iv) Multi-language UI infrastructure (i18n bundles, lint rule) — MIT.
Please list any proprietary components developed through the workplan:
None. Every new component developed during the UNICEF-funded period will be released under an OSI-approved permissive licence. Licensing follows the existing repo convention: MIT for applications and libraries (apps/web, apps/api, apps/indexer, packages/stealth, packages/config, packages/types, packages/eslint-config); Apache-2.0 for smart contracts and pool SDK (packages/contracts, packages/pool — inherited from 0xbow upstream). The repository will be made public by month six. The only non-public elements are: (a) operational pilot configuration data (kept private for beneficiary safety, not as IP); (b) commercial agreements with paying ASP-attestation customers (contracts, not code).
Note on A5: Administrator: Include as many milestones and activities as you need to keep the consistency along the project design.