## Tab 1 Project Design Budget
TEMPLATE 7 Tab 1: PROJECT DESIGN BUDGET
Company Name: | Cartagena On Chain
TIMELINE | TASKS | BUDGET
| What are the major milestones you expect to achieve with the UNICEF Innovation Fund investment? What specific activities will you carry out to reach each milestone? Please complete your budget using the same milestones and activities listed in Template 3 (Project Design Statement & Data Plan). Budgets that do not align with the milestones and activities in Template 3 will not be considered. | This budget should detail the costs to be covered by the UNICEF Venture Fund investment. Each budget line must be linked to the corresponding activity listed in Column B (TASKS). Formulas have been provided—if you add additional rows, please ensure the formulas remain accurate. Use the blue fields to calculate the total budget per quarter, and verify that the formula also reflects the total for the full 12-month period. For each milestone, indicate the amount of funding requested in Column C (USD) or Column D (ETH)—choose only one currency per activity, not both.
Currency |  | USD
Quarter 1 Total
Milestone 1 | Engineering rigor & ERC-20 pool deployment (current production chain)
Activity 1 | Activity 1 — Coverage tooling installed; baseline coverage report published | 3000
Activity 2 | Activity 2 — Deploy ERC-20 stablecoin pool to current production chain; round-trip test | 6000
Milestone 2 | External security delta-audit kickoff (Galeon-specific contracts + stealth library)
Activity 1 | Activity 1 — Solicit proposals; select firm; sign engagement letter; initial retainer | 4000
Activity 2 | Activity 2 — Freeze audit branch; produce threat model and modifications diff | 1500
Milestone 3 | Partner discovery, LOI, and operational model scoping
Activity 1 | Activity 1 — Discovery sessions with UNICEF country offices and NGO partners | 2500
Activity 2 | Activity 2 — Sign LOI; draft operational dependency model; legal review of LOI/partnership terms | 3000
Milestone 4 | Beneficiary onboarding — embedded email-based wallet and gas-simplification options
Activity 1 | Activity 1 — Integrate Privy SDK (or equivalent) with email recovery; evaluate gas-simplification options | 6500
Activity 2 | Activity 2 — Mobile-first redesign of Setup, Receive, Pay, Collect for non-technical first-time users | 2750
Quarter 2 total
Milestone 1 | Real ASP filtering — sanctions screening + blocklist (replaces hackathon auto-approve)
Activity 1 | Activity 1 — Select & integrate screening provider; rejection-handling protocol; ragequit test | 5500
Activity 2 | Activity 2 — Publish ASP policy + appeals process; start IPFS attestation publication | 3500
Milestone 2 | Audit findings remediated; final audit report published
Activity 1 | Activity 1 — Triage findings; assign owners; plan remediation | 8000
Activity 2 | Activity 2 — Implement fixes; auditor re-review; publish final report and letter of resolution | 13000
Milestone 3 | Children's data protection — DPIA review and in-product safeguards
Activity 1 | Activity 1 — Engage external privacy counsel; DPIA review aligned with UNICEF ethical standards | 3000
Activity 2 | Activity 2 — Implement children_program_mode flag; audit-log surface; data-minimisation contract | 3500
Milestone 4 | Open-source community readiness + sandbox with partner staff
Activity 1 | Activity 1 — Security review of public repo; secrets audit; UNICEF attribution; community guides | 2750
Activity 2 | Activity 2 — Sandbox testing with partner staff: staging env, test-token faucet, training, runbook | 5000
Quarter 3 total
Milestone 1 | Controlled pilot launch with LOI partner (≤50 beneficiaries)
Activity 1 | Activity 1 — Production pilot deployment; monitoring; runbook for partner staff | 4150
Activity 2 | Activity 2 — Onboard first cohort; monitor; collect feedback after 2 weeks | 3000
Milestone 2 | Shipwreck jurisdiction expansion and multi-language UI (English + one pilot language)
Activity 1 | Activity 1 — Extract user-facing strings; pilot-language support (partner / in-house) | 1500
Activity 2 | Activity 2 — Add pilot-jurisdiction Shipwreck template; integrate documented exchange-rate source; jurisdiction memo | 3500
Milestone 3 | Pilot validation and feedback
Activity 1 | Activity 1 — Ethics-cleared interviews with beneficiaries and partner staff | 1500
Activity 2 | Activity 2 — Usability tests on Pay and Collect flows | 1000
Milestone 4 | N/A
Activity 1 | N/A
Activity 2 | N/A
Quarter 4 total
Milestone 1 | Pilot expansion to ≤100 beneficiaries
Activity 1 | Activity 1 — Implement top fixes from Q3 feedback; expand partner staff training | 2500
Activity 2 | Activity 2 — Onboard second cohort; monitor for 30 days | 2600
Milestone 2 | Implementation and usability evaluation co-conducted with partner M&E lead
Activity 1 | Activity 1 — Co-conduct evaluation with partner M&E lead following partner methodology | 750
Activity 2 | Activity 2 — Publish implementation-evaluation.pdf jointly with partner | 750
Milestone 3 | Developer documentation and integration guides
Activity 1 | Activity 1 — Write protocol overview, API reference, security model, FAQ | 1500
Activity 2 | Activity 2 — Two end-to-end integration tutorials | 1500
Milestone 4 | Sustainability roadmap, partner engagement, and final validation + accessibility conformance review
Activity 1 | Activity 1 — Document sustainability plan; open conversations with prospective post-funding partners | 1500
Activity 2 | Activity 2 — Final validation sessions + WCAG 2.1 AA conformance review (in-house using standard tooling) | 750

## Tab 2 Company 1-YR Budget
TEMPLATE 7, Tab 2: COMPANY 1-YR BUDGET |  |  | Direction: please complete the company budget and indicate amounts received, held or expended in the appropriate currency. Do not convert each line into each currency.
Budget Period: 12-month period beginning at contract execution (subject to UNICEF award)
Company Name: Cartagena On Chain | USD |  |  | ETH
| Year 1: Month 1- Month 6 | Year 1: Month7- Month 12 | TOTAL BUDGET AMOUNT IN USD | Year 1: Month 1- Month 6 | Year 1: Month7- Month 12 | TOTAL BUDGET AMOUNT IN ETH
Expected Income
Operating Income [List detailed budget items in rows below. See example sheet for suggestions]
No current operating revenue from the Galeon project | 0 | 0
Non-Operating Income [List detailed budget items in rows below (see example sheet for suggestions).
UNICEF Innovation Fund grant (if awarded) | 73500 | 26500
TOTAL INCOME
Salaries & Wages (engineering + operational team) | 48000 | 23500
General & Administration (legal counsel, infrastructure) | 5500 | 3000
External security delta-audit (Galeon-specific contracts, ASP changes, UUPS, stealth library) | 20000 | 0
TOTAL EXPENSE
Net Income Before Tax
Income Tax Expense | 0 | 0
NET INCOME

## EXAMPLE COMPANY 1YR BUDGET
BUDGET FIGURES GIVEN ARE ONLY ILLUSTRATIVE AND NOT INDICATIVE OF INFORMATION OR TRENDS THAT WILL BE ASSESSED FAVOURABLY DURING SCORING.
Budget Period: XXXX 2020 to XXXX 2020
| Year 1: Month 1- Month 6 | Year 1: Month7- Month 12 | TOTAL BUDGET AMOUNT
Expected Income
Operating Income
Revenue from Sales | 5000 | 7500
Other
Non-Operating Income
Capital Contribution | 20000 | 20000
Investment | 45000 | 45000
Donations | 0 | 0
Other
TOTAL INCOME
Expenses
Salaries & Wages | 50000 | 60000
General & Administration | 5000 | 5000
Marketing & Distribution | 1000 | 1000
Manufacturing | 4500 | 6000
Other
TOTAL EXPENSE
Net Income Before Tax
Income Tax Expense
NET INCOME